## Sheet1
PROJECT:	PACMAN SFML 2014				Started 5.2.2014

TODO				DONE	DATE
Update sprite position based on key input				x	6.2.2014
Create dot				x	8.2.2014
Draw dot				x	8.2.2014
Consume dot when moved upon				x	8.2.2014
Create enemy				x	9.2.2014
Draw score				x	8.2.2014
Update score when dot is consumed				x	9.2.2014
Basic enemy AI				x	17.2.2014
A* path finder				x	16.2.2014
Make enemy follow path				x	17.2.2014
Improve path finding performance (threading)				x	22.2.2014
Smooth based movement for player				x	25.2.2014
Advanced AI (behaviours)				x	16.3.2014
Improve path finding performance (limit simultaneous requests by queueing)				DONT
Improve path finding performance (global static graph)				x	22.2.2014
Smooth based movement for enemy				x	26.2.2014
Player should be able turn more smoothly				x	27.2.2014
Player turning in crossroads should skip center tile				DONT
Remove dead ends from level (add teleports)				x	17.3.2014
Remove excess AI turning				x	16.3.2014
If enemy is at a crossroad, prevent reversing if new path requires direction change				DONT
Create Blinky chase behaviour				x	18.3.2014
Create Pinky chase behaviour				x	18.3.2014
Create Inky chase behaviour				x	19.3.2014
Create Clyde chase behaviour				x	19.3.2014
Create enemy scatter behaviour				x	18.3.2014
Make enemies 5-10% slower than Pacman				x	20.3.2014
Stop Pacman movement for one frame after dot is eaten				x	30.3.2014
Slow ghost speed by 30-50% when frightened				x	25.3.2014
Enemies should start at center and be activated after each other				x	31.3.2014
Switch to frightened mode when energizer is eaten				x	25.3.2014
Add Pacman extra lives				x	11.4.2014
Player should lose one life and restart position when hit by ghost				x	11.4.2014
Ghost should move to center when eaten in frightened mode				x	30.3.2014
Implement sprite sheet animator				x	19.4.2014
Add ghost animations				x	22.4.2014
Add Pacman animations				x	20.4.2014
Set window and game viewport dimensions				x	20.4.2014
Add start menu				x	4.5.2014
Add basic sound effects				x	7.5.2014
Keep ghosts in single tile while in pen and animate movement instead				DONT
Fine tune score and player lives GUI element placement				x	23.4.2014
Pause game for a short while after player death				x	4.5.2014
Replace ghost and pacman sprite sheets with better versions
Add game over menu				x	4.5.2014
Create audio manager				x	7.5.2014
Restart level once all dots eaten				x	10.5.2014
Pause menu (Restart/Exit/Continue)				x	4.5.2014
Main menu (Play/Credits/Exit)				x	4.5.2014
Add credits menu/list				x	17.5.2014
BUG: Enemy movement motor sometimes cannot decide next direction, reset somehow?				FIXED?
Add bonus symbol				DONT
Increase difficulty settings on each new level change				x	17.5.2014
Improve/add SFX				x	17.5.2014
BUG: Enemy ghost doesn't always get eaten when collision happens, check nearby tiles?				FIXED?
Make easy install/package from game files				x	18.5.2014
Add version/revision information				x	18.5.2014
BUG: Enemy gets stuck at ghost entry for the remainder of game
On level start, Pacman mouth should open only when starting to move				x	22.5.2014
Move Pacman mouth always when moving				x	22.5.2014
Add new ghost eaten sound				x	18.6.2014
Ghost flickering when frightened?
Shortcut doesn't work (Release build, Win 8)
Option to mute audio				x	22.5.2014
Difficulty should increase behaviour timer also?
Player should start slight offset so texture is set between tiles				x	22.5.2014
Increase AI difficulty by using player position as chase position, if default position is not accessible?
Energizer flickering, to make eating harder?
Compress audio
AI should not reset to scatter mode after frightened, but resume on previous behaviour